## PURPOSE:

To provide for a uniform process for the intake of T&C projects at CSU Channel Islands.

## BACKGROUND:

T&C is required to complete projects in order to support the University mission. To be efficient and effective at planning and managing project activities using the limited resources that are available, T&C must adopt standard practices to guide projects and keep them on target.

The lifecycle of T&C projects is as follows:

Phase 1. Intake

Phase 2. Planning

Phase 3. Execution & Monitoring

Phase 4. Closure & Hand-Off

## BUSINESS PRACTICE:

### Accountability*:*

The Chief Information Officer and T&C managers

### Applicability:

All T&C employees

### Definitions:

1. **Operations**. Steady-state T&C activities used to support existing products and services. They are repetitive, with the same outcomes, and are ongoing, with no start or end dates.
2. **Project**. A temporary endeavor undertaken to create or update a unique product, service, or result. In particular, a project in T&C is undertaken to create a new service that has not existed before. A project has a definitive beginning and end, and measurable outcomes and results. Projects are further defined by their size and scope.
3. **Supervising Manager**. The T&C manager who is ultimately responsible for the project, and has ownership of the project charter.
4. **Project Lead**. The T&C manager or staff member responsible for performing project management tasks for the duration of the project. Depending on the scope and size of the project, the Project Management Office may provide project lead, or the Supervising Manager will assume day-to-day project management responsibilities.
5. **Project Management Office (PMO)**. The T&C team responsible for the coordination, support and guidance of T&C projects.
6. **Project Review Board**. A group of T&C employees, designated by the CIO, which reviews projects and makes recommendations to the CIO.

### Text:

#### Project Attributes

In general, projects are—

* *Specific*. A project has a specific purpose, set of requirements, and scope of work defined.
* *Measurable*. A project’s success can be quantified; T&C and project management can tell when specific milestones have been reached.
* *Approved*. A project must receive the approval of T&C Governance and affected stakeholders so that resources are made available to execute the project. Changes to project timelines or scope must also receive approval from governance and affected stakeholders.
* *Realistic*. Projects can be completed with resources that are, or will be made available. Resources include time, funding, goodwill and knowledge.
* *Time*-*bound.* Projects are temporary, and have definitive start and end dates.

In contrast, operations are everyday business processes. They are repetitive, with the same outcomes, and are ongoing, with no start or end dates. Operations support activities typically are completed in 10 hours or less. It is the responsibility of the T&C manager to determine if a set of activities constitutes a project or not.

#### Project Classes

T&C projects will be categorized into 3 classes. Classes are determined based on resources required, impact and complexity. Project class will be documented in the Project Charter.

|  |  |  |
| --- | --- | --- |
| **Description** | **Project Size / Complexity** | **T&C staff time (in hours)** |
| Class 1 | Small / Simple | 10 to 30 |
| Class 2 | Medium / Medium | 31 to 100 |
| Class 3 | Large / Complex | 100 or more  |

#### Project Intake Lead Time

All new project requests submitted to T&C must include sufficient lead time to complete the project intake and approval process. Actual lead time required depends on the size and complexity of project, as well as the availability of resources to complete project intake activities. Minimum lead time is 4 weeks (6 weeks recommended).

#### Phase 1 - Intake

The T&C project management process begins with the Intake Phase. Project intake consists of the following steps:

1. A request for a new project is received by T&C either through formal, semi-formal or informal means.
2. An T&C manager is assigned as Supervising Manager to the project request by the CIO.
3. The Supervising Manager (or CIO) selects the Project Lead. The Project Lead may be the Supervising Manager, or a designee.
4. The Supervising Manager reviews the initial request, meets with the project’s client, and determines whether to proceed, postpone, or cancel the request.
5. The Supervising Manager (or Project Lead) gathers information necessary to complete the Project Charter, completes the Project Charter form, and submits it to the Project Management Office. The submission of a Project Charter implies the Supervising Manager’s approval for the project to proceed.
6. The PMO adds the project charter to the T&C project database and calendar
7. PMO reviews the Project Charter and may refer the Charter back to the Supervising Manager for additional information.
8. Supervising Manager completes required project management and approval tasks.
	1. A Class 1 project needs no further approval; the approval of the submitting Supervising Manager is all that is required to proceed.
	2. A Class 2 project requires the approval of the CIO.
	3. A Class 3 project must be reviewed by the Project Review Board and approved by the CIO. In addition, a Class 3 project may require additional approvals outside T&C, at the discretion of the CIO.
9. PMO will meet regularly with the CIO to review submitted projects and their approval status.
10. PMO notes the approval in project database and the project may proceed to the next phase.
	1. Class 1 projects may proceed directly to Phase 3 (Execution); however, completing some Phase 2 (Planning) activities is recommended for ensuring project success.
	2. Class 2 or Class 3 project must complete all Phase 2 planning activities required for projects of their scope.

### Exhibits

Project Intake Flowcharts: [www.csuci.edu/it/projects/](http://www.csuci.edu/it/projects/)
Project Database and Calendar: <http://sharepoint/sites/its/SiteDirectory/ait-projects>

*The following documents are incorporated by reference. Please visit* [*www.csuci.edu/it/projects/*](http://www.csuci.edu/it/projects/) *for the latest versions.*

Project Charter Form

## Related Resources

*Business Process on Project Planning*

*Business Process on Project Execution & Monitoring*

*Business Process on Project Closure & Hand-Off*