## Sheet1
Human Resources Content Management Kaizen Control Plan
Who | Control Item | Measurement | Reporting Cycle | Implementation Date/Start Date | Baseline Data | Target | Reporting Period | Actual Measurement | Range of Acceptance | Corrective Action Needed | Cause | Solution | % Complete | Solution Implementation Date
HR Manager | Benefits Packets | Packets contain documents identified in new policy 100% | Monthly | 2018-11-24 | 100% compliance | 100% compliance | 30 days |  | 100% compliance
[7 empty] | 60 days |  | 100% compliance
[7 empty] | 90 days |  | 100% compliance
[7 empty] | 120 days |  | 100% compliance
[7 empty] | 150 days |  | 100% compliance
[7 empty] | 180 days |  | 100% compliance
Note on F3: Human Resources: Baseline Data: Information as of Implementation date
Note on I4: Human Resources: Benefits Packets Actual Measurement: Obtain a sample of the Benefit Packets from each office site. Manually review packets against the Packet Policy document and report percentage in compliance
Note on K3: Human Rsources: Corrective Action Needed: Yes or No Answer
Note on L3: Human Resources: Examples of Causes: - Unclear procedures or processes - User training not effective - Performance problems (Systems are manual or automated) - Support to Users Lacking - Old Habits die hard - New understanding or information identified that impacts policy/process negatively (rework needed)
Note on M3: Human Resources: Examples of Solutions: - Rework process/policy - Refresher Training - Walk staff through process - Add additional support to Staff - Rework processes - Clarify procedures/policy
Note on N3: Human Resources: % Complete: Percent Completed for Solution