## Action Log
CAMPUS READING CELEBRATION
Thursday, October 10, 2013
ACTION ITEMS | NOTES | TO DO | Due | Completed
LOCATION
| Grand Salon | 25Live Request | July | 2013-06-06
| 400 Chairs - Theatre layout | Create Layout Map | July | 2013-07-11
|  | Send layout map to all Vendors/Service Providers | September
PARKING
|  | El Dorado Parking Lot Rental requested | July | 2013-06-06
|  | Directional Signs | July | 2013-06-06
|  | 1 Reserved spot all day for Author near Grand Salon | July | 2013-06-06
|  | Free VISTA bus requested | July | 2013-06-06
|  | Check-in with Danny to confirm all services | September
|  | Emily turn in Signage | 2013-10-07
C&M
| Tom - Marketing plan | Contact Tom regarding Save the Date | July | 2013-06-26
|  | Complete C&M project request form | July | 2013-07-11
|  | Submit Event News Release Request | August | 2013-09-05
|  | Contact Tom about Web Button, Banner, Bookmark designs | August | 2013-07-18
|  | Email Tom Marketing Plan | August | 2013-07-18
|  | Reserve banner frames (2) | August | 2013-07-11
|  | Reserve Flags from Joanna (Check-in, Welcome, Restroom) & Seal | September | 2013-07-11
|  | Request approval for Web Button | August | 2013-07-18
|  | Place Web Button from 9/1-10/10 | August | 2013-08-12
|  | Confirm Joanna is photographing event | September
|  | Pickup Banner Frames | 2013-09-26
|  | Email Joanna event agenda | 2013-10-07
|  | Pickup Flags/Seal/Photo Backdrop from Joanna | 2013-10-09
RENTALS
| Party Pleasers = Rentals | Place order with Party Pleasers | September | 2013-09-10
| Linens only | Pay Party Pleasers with CC | 2013-10-10
AUDIO/VISUAL/LIGHTING
| Luners = Sound/Screens/Lighting | Request quotes for AV needs | August | 2013-08-29
|  | Place Order | August
|  | Luners RGS | August
|  | Get Authors presentataion for testing | 2013-10-07
FLOWERS
| Flower Power = Flowers | Place Flower Power order | September | 2013-09-10
| 1 Podium Piece; 2 Buffet Pieces | Flower Power RGS | September
CATERING
| Dessert Reception | Request catering quote (All white linen) | August
| - coffee | Finalize Accounting Strings between AA and SA for catering | September
|  | Place catering order | September
EVENT LOGISTICS
| Bookstore selling books | Confirm Bookstore logistics with Fah (RE: Selling books at event) | August | 2013-08-19
| Book signing | Update CRC website | August | 2013-06-06
|  | Place event on CI Homepage | August | 2013-08-15
|  | Place request for Wavelength | September | 2013-09-05
|  | Email PowerPoint ads to Library & SUB | September | 2013-09-05
|  | Create Event Agenda | September
|  | Email Author with presentation questions | September
|  | Place Banners out (University Dr Entrance & Library) | 2013-09-30
|  | Collect Authors Presentation matierials (PowerPoint) | 2013-10-07
PRINTING
| (4) Banners; posters - Uglen&Campus; Bookmarks | Request Jano Graphic Quote for Bookmarks | August | 2013-08-19
|  | Jano Graphics RGS | September
|  | Place order with BIG SHOTS for Banners & Posters | 2013-08-20
REGISTRATION
| Online live on 9/1/13 | Place eMarket Request to AP | July | 2013-06-10
|  | Meet with AP before Live date for TESTING | 2013-08-27 | 2013-08-18
|  | Add Registration link to Website & 25Live | August | 2013-08-19
|  | Ask about iPad CC Swipers | August | NO
|  | Request Petty Cash from Beatriz | September | 2013-09-05
|  | Pickup Cash | 2013-10-09
|  | Export Final List | 2013-10-10
|  | Create Check-in Lists for Event | 2013-10-10
VOLUNTEERS
|  | Request Volunteers (Karen email global) | September
|  | Email Annette P. to ask for student volunteers | September
|  | Send meeting proposal to volunteers | 2013-09-20
|  | Print instructions for volunteers | 2013-10-07
|  | Bring iPads to event | 2013-10-10

## Budget
Daniel Lee Music Fest
2015
Item | Estimated Budget 4/15 | Notes
Rentals: Stage/lighting | 500 | final
IT Chargeback: on-site technician | 0
Parking Chargeback: 100 community; signage | 100
Printing: Posters; bookmarks;kiosk | 450
Catering: Refreshments | 1200
CD Generation
Musicians | 3000
Misc. (In-State Travel) | 250
Estimated Total: | 5500
Ticket Sale Revenue:
Grand Total:

## Day of Actions
Campus Reading Celebration
Thursday, October 10, 2013
Day of Actions
10:00am
Oversee Grand Salon set-up (Wed. also)
Bring to Grand Salon:
|  | *Extra Posters | **Move library banner to North Quad entrance across from ELD
*Bookmarks
*Registration Lists
*Registration Signage/flag
*Restroom Signage
*Welcome Flags
*Presidential Seal
*Background Music
*Pens/Highlighters/Nice pen for booksigning
*Camarillo Sponsorship Banner
*Reserved stickers
*10 seats/tickets for City of Camarillo
*Cash Box (Cash)
*Water Bottles
*Copy of Agenda for Podium
*(3) Standing Whiteboard signs for registration
Place up lights and test them
3:00pm
Catering set-up starts
*All white linens inside Grand Salon
Place Reserved stickers on front row seats
Set-up Registration Tables
Place restroom signage
Set-up (1) Welcome Flag at entrance from Road
Set-up (1) Welcome Flag at entrance to Grand Salon
Set-up (1) Restroom Flag at entrance to Del Norte
Place copy of agenda at podium
Place water bottles at podium
4:00pm
Flower Power Delivery
Emily arrives at 4:15ish
5:30pm
Volunteers arrive
Bookstore arrives
6:00pm
Doors/Registration open
6:30pm
Que Speaker to begin
7:00pm
Switch Registration tables for Book Signing
Place water bottle at book signing table

## Volunteers
Campus Reading Celebration
Volunteers
Last Name | First Name | Role
Registration
Registration
Registration
Registration
Introduce Pres. Rush
Introduce Junot Diaz
Registration - payments
Registration-payments